## Estimation
No | Modules/Page | Items | Status | PIC | Note
SCHEDULES
| - Layout | Create search module layout | 100%
| - Layout | create filter order status module layout | 100%
| - Layout | Create table listed all order | 100%
| - Layout | Change style color of order by order status | 80%
| - Function | Filter order by order status | 50%
| - Function | Search order by name or order No | 0%
| - Function | Get list order by default ( no filter and search) | 100%
| - Function | Get list order by filter | 0%
| - Function | Get list order by search name | 0%
| - Function | Get List order by search order No | 0%
| - Function | Check excel file if uploaded for customer Name/Number | 100%
| - Function | Check apparels order | 100%
| - Function | Get apparel info for order list | 50%
| - Function | Generate tracking number | 0%
| - Function | Check Artwork is attached | 100%
| - Function | Function to change status for Proof approve | 100%
| - Function | Check payment | 0%
ORDER
| - Layout | Create overview order info module | 80%
| - Layout | Create Art information | 20%
| - Layout | Create Shipping information | 100%
| - Layout | Create Billing information | 100%
| - Function | Get order overview detail | 70%
| - Function | Get size information | 70%
| - Function | Get artwork image review | 60%
| - Function | Get shipping informaiton | 100%
| - Function | Get billing detail | 100%
| - Function | Create new function for comment/note | 0%
| - Function | Create new fucntion upload excel file for customer name/number | 20%
| - Function | Create new fucntion download Artwork | 10%
GARMENT
| - Layout | Create list order | 0%
| - Layout | Create view to add new garment for order | 0%
| - Function | Get list of order garment detail | 0%
| - Function | Create function add new garment | 0%
| - Function | Create fucntion manager garment | 0%
| - Function | Create fucntion manager distrubutor | 0%
Sumary