## Estimation
No | Modules/Page | Items | working hours | Status | Note
MAIN ORDER DETAIL
|  | Change order number to TVP2000 | 2
|  | Change Date and time format | 1
|  | Edit shiping button link to shiping page | 1
|  | Create comment box | 0
GARMENT
|  | Create function to add many row | 3
|  | Create function to calculator total cost | 3
|  | Add delete button for earch row | 2
|  | Change order # to invoice | 1
ARTWORK
|  | create new artwork layout | 4
|  | Function get detail artwork to display | 4
|  | Create function add font and back color | 2
|  | Create function change font and back color | 2
|  | Create upload artwork function for front | 3
|  | Create upload artwork function for back | 3
|  | Auto add activity history to comment box after save | 2
|  | Create function to remove artwork uploaded file | 2
|  | Display comment box in this page | 2
PROOF
|  | Create new UI layout for proof | 4
|  | Function get detail proof to display | 4
|  | Create upload proof function | 3
|  | Auto add activity history to comment box after save | 2
|  | Create function to remove proof uploaded file | 2
|  | Create function to approve Proof | 2
|  | Display comment box in this page | 2
SHIP DATE
|  | Create new UI layout for change ship date | 3
|  | Function get detail proof to display | 4
|  | create function change shiping date and update original date | 2
|  | Create fucntion to approve shiping date | 2
|  | Auto add activity history to comment box after save | 2
|  | Display comment box in this page | 2
READY TO PRINT
|  | Create new UI layout for ready to print page | 4
|  | Function get order detail | 4
|  | Function to get proof and display | 3
|  | Add print order button | 2
|  | Display comment box in this page | 2
PRINT ORDER
|  | Create layout UI for print page | 8
|  | Function to get print information | 4
|  | Add information proof and order detail to create printable page (pdf file) | 4
Sumary |  |  | 102