## Estimation
No | Modules/Page | Items | Man/days | PIC | Note
SCHEDULES
| - Layout | Create search module layout | 1
| - Layout | create filter order status module layout | 1
| - Layout | Create table listed all order | 2
| - Layout | Change style color of order by order status | 2
| - Function | Filter order by order status | 1
| - Function | Search order by name or order No | 1
| - Function | Get list order by default ( no filter and search) | 1
| - Function | Get list order by filter | 1
| - Function | Get list order by search name | 1
| - Function | Get List order by search order No | 1
| - Function | Check excel file if uploaded for customer Name/Number | 2
| - Function | Check apparels order | 2
| - Function | Get apparel info for order list | 1
| - Function | Generate tracking number | 1
| - Function | Check Artwork is attached | 1
| - Function | Function to change status for Proof approve | 2
| - Function | Check payment | 2
ORDER
| - Layout | Create overview order info module | 1
| - Layout | Create Art information | 2
| - Layout | Create Shipping information | 1
| - Layout | Create Billing information | 1
| - Function | Get order overview detail | 1
| - Function | Get size information | 1
| - Function | Get artwork image review | 2
| - Function | Get shipping informaiton | 1
| - Function | Get billing detail | 1
| - Function | Create new function for comment/note | 2
| - Function | Create new fucntion upload excel file for customer name/number | 2
| - Function | Create new fucntion download Artwork | 3
GARMENT
| - Layout | Create list order | 2
| - Layout | Create view to add new garment for order | 2
| - Function | Get list of order garment detail | 2
| - Function | Create function add new garment | 2
| - Function | Create fucntion manager garment | 1
| - Function | Create fucntion manager distrubutor | 2
Sumary |  | 52